## Action Plan
Action Plan for LoRa production
Sl No | Action Plan | Responsbility | Target Date | Remarks | Work Status | Completed Date
1 | Nsoft to Purchase Battery 3.6V from Ultra life Batteries, Whitefield | Naveen/Gouse | 2017-09-15 | 5 nos to purchased | Completed | 2017-09-15
2 | Nsoft to Purchase Battery holder for the above | Naveen | 2017-09-14 | ProtoCentral; | Completed | 2017-09-14
3 | Nsoft to purchase J4 comp interface connector for battery from SP road | Naveen | 2017-09-14 | If battery holder is purchased, then this comp not required | Completed | 2017-09-14
4 | Nsoft to test Node with op volt 3V and big antenna and AA battery with 3.6V | Naveen | 2017-09-16 | With 1m gateway antenna; 3V working | Completed | 2017-09-16
6 | Nsoft to confirm Kaynes assembly of 100 Nodes | Naveen | 2017-09-16 | only after testing with new battery | Completed | 2017-09-18
7 | Kaynes to ship UJ2 USB comp for LPU | Naveen | 2017-09-14 | 5 nos
8 | Gouse to update all BoM once again, so that in future we don't miss any components while procuring. | Gouse | 2017-09-17 | Since many items have been manually assembled in PCB, were these comp available in BoM?
9 | Gouse to train LoRa programming to Nsoft; with Keil 5 | Gouse | 2017-09-17
10 | Nsoft & Gouse to visit Arrow Asia for discussion regarding meter programming & hardware support. | Gouse/Nsoft | 2017-09-21 | Meeting scheduled on 21-09-2017
11 | Water meter shipment | Naveen | 2017-09-15 | Delivered | Completed | 2017-09-15
12 | 110 Antennas shipped from IMST | Naveen |  | Expecting delivery on 18-09-2017 | In progress
13 | Kaynes to deliver 2 GW module | Naveen |  | Follow up; Stencils manufacturing in progress in Chennai | In progress
14 | Fides to deliver UFL-SMA connector cable | Naveen | 2017-09-14 | Delivered 110 nos | Completed | 2017-09-14
15 | LPU Assembly & loading Linux & Testing | Gouse | 2017-09-20 |  | In progress
16 | LPU PCB layout to be redesigned as there is a mechnical issue in mounting GPRS module. | Gouse |  | Current 5 nos can be resolved by manual removal of a component and mounting.
17 | Re-manufacture LPU PCB for Rev3.0 from PCB Power | Naveen/Gouse |  | Gouse to share Fab file, Assy file & BoM list of new design Rev3.0
18 | Water meter M-Bus protocol address mapping file required | Naveen |  | Requested Zenner; Shared Pulse connection; expecting Mapping address for M-bus | In progress
19 | MCP1700 component for 3V to be procured | Naveen/Gouse | 2017-09-18 | Gouse to share the link in Mouser | Completed | 2017-09-18
20 | Kaynes not mounted TSSOP comp in Node Rev2.0
21 | Kaynes says UJ2 USB comp not available with them; |  |  | Escalated to Mr.Jayaram
22 | Nsoft to Procure MCP1700 comp from Mouser | Naveen | 2017-09-18 | Expecting delivery on 23-09-2017 | Completed | 2017-09-18
23